## Timeline
Task/Assignment | Assigned | Start Date | Duration (weeks) | Due Date | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  | Phase 4 |  |  | Phase 5 |  |  | Phase 6
[5 empty] | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
[5 empty] | 2023-09-03 | 2023-09-10 | 2023-09-17 | 2023-09-24 | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19 | 2023-11-26 | 2023-12-03 | 2023-12-10 | 2023-12-17
Conceive and propose project | All | 2023-09-03 | 2 | 2023-09-17
Project presentation (in class) | All | 2023-09-17 | 0 | 2023-09-17
Create initial Software Project Management Plan (SPMP) | All | 2023-09-17 | 3 | 2023-10-08
Create github team/organization for project | Jocelyn | 2023-09-17 | 0 | 2023-09-17
Order hardware for project use | All | 2023-09-24 | 2 | 2023-10-08
Verify hardware functionality | All | 2023-10-01 | 2 | 2023-10-15
Setup micro-python development env. and github repos | Jocelyn | 2023-10-01 | 1 | 2023-10-08
Setup Xcode Project and github repos | Jocelyn | 2023-10-01 | 1 | 2023-10-08
Setup Django project and github repos | Jocelyn | 2023-10-01 | 1 | 2023-10-08
Solidify requirements for display firmware | All | 2023-10-08 | 2 | 2023-10-22
Solidify requirements for iOS & Web apps | All | 2023-10-08 | 2 | 2023-10-22
Write Software Requirements doc (SRS) | All | 2023-10-08 | 2 | 2023-10-22
UI/UX mockups for web app | Shrey | 2023-10-15 | 2 | 2023-10-29
UI/UX mockups for iOS | Jocelyn | 2023-10-15 | 2 | 2023-10-29
Define color conversion algorithm for e-paper display | All | 2023-10-15 | 2 | 2023-10-29
Define wifi/BT data upload protocols | All | 2023-10-08 | 3 | 2023-10-29
Code wifi data upload module (web app) | Shrey, Erick | 2023-10-22 | 3 | 2023-11-12
Code wifi data upload module (iOS app) | Jocelyn, Michael | 2023-10-22 | 3 | 2023-11-12
Implement UI for web app | Erick, Shrey | 2023-10-22 | 3 | 2023-11-12
Implement UI for iOS app | Michael, Jocelyn | 2023-10-22 | 3 | 2023-11-12
Prepare for Code review #1 | All | 2023-11-05 | 1 | 2023-11-12
Define code/unit test for web & iOS apps | Michael, Erick | 2023-10-29 | 2 | 2023-11-12
Write Software Design Doc (SDS) | All | 2023-10-29 | 2 | 2023-11-12
Code unit tests for web app | Erick | 2023-11-11 | 3 | 2023-12-02
Code unit tests for iOS app | Michael | 2023-11-11 | 3 | 2023-12-02
Code unit tests for rp2040/Display | Michael, Erick | 2023-11-11 | 3 | 2023-12-02
Code integration tests for iOS app | Jocelyn | 2023-11-25 | 2 | 2023-12-09
Code integration tests for web app | Shrey | 2023-11-25 | 2 | 2023-12-09
Code review #2 | All | 2023-12-03 | 2 | 2023-12-17
Write Software Test Plan (STP) doc | All | 2023-12-03 | 2 | 2023-12-17
Prepare for End of semester demo | All | 2023-12-03 | 2 | 2023-12-17
Project presentation/demo (in class) | ALL | 2023-12-17 | 0 | 2023-12-17
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0

## Tasks
Task | Assigned | Due Date | Duration (Est. Wks) | Adjusted Start
Conceive and propose project | All | 2023-09-17 | 2 | 2023-09-03
Project presentation (in class) | All | 2023-09-17 | 0 | 2023-09-17
Create initial Software Project Management Plan (SPMP) | All | 2023-10-08 | 3 | 2023-09-17
Create github team/organization for project | Jocelyn | 2023-09-17 | 0 | 2023-09-17
Order hardware for project use | All | 2023-10-08 | 2 | 2023-09-24
Verify hardware functionality | All | 2023-10-15 | 2 | 2023-10-01
Setup micro-python development env. and github repos | Jocelyn | 2023-10-08 | 1 | 2023-10-01
Setup Xcode Project and github repos | Jocelyn | 2023-10-08 | 1 | 2023-10-01
Setup Django project and github repos | Jocelyn | 2023-10-08 | 1 | 2023-10-01
Solidify requirements for display firmware | All | 2023-10-22 | 2 | 2023-10-08
Solidify requirements for iOS & Web apps | All | 2023-10-22 | 2 | 2023-10-08
Write Software Requirements doc (SRS) | All | 2023-10-22 | 2 | 2023-10-08
UI/UX mockups for web app | Shrey | 2023-10-29 | 2 | 2023-10-15
UI/UX mockups for iOS | Jocelyn | 2023-10-29 | 2 | 2023-10-15
Define color conversion algorithm for e-paper display | All | 2023-10-29 | 2 | 2023-10-15
Define wifi/BT data upload protocols | All | 2023-10-29 | 3 | 2023-10-08
Code wifi data upload module (web app) | Shrey, Erick | 2023-11-12 | 3 | 2023-10-22
Code wifi data upload module (iOS app) | Jocelyn, Michael | 2023-11-12 | 3 | 2023-10-22
Implement UI for web app | Erick, Shrey | 2023-11-12 | 3 | 2023-10-22
Implement UI for iOS app | Michael, Jocelyn | 2023-11-12 | 3 | 2023-10-22
Prepare for Code review #1 | All | 2023-11-12 | 1 | 2023-11-05
Define code/unit test for web & iOS apps | Michael, Erick | 2023-11-12 | 2 | 2023-10-29
Write Software Design Doc (SDS) | All | 2023-11-12 | 2 | 2023-10-29
Code unit tests for web app | Erick | 2023-12-02 | 3 | 2023-11-11
Code unit tests for iOS app | Michael | 2023-12-02 | 3 | 2023-11-11
Code unit tests for rp2040/Display | Michael, Erick | 2023-12-02 | 3 | 2023-11-11
Code integration tests for iOS app | Jocelyn | 2023-12-09 | 2 | 2023-11-25
Code integration tests for web app | Shrey | 2023-12-09 | 2 | 2023-11-25
Code review #2 | All | 2023-12-17 | 2 | 2023-12-03
Write Software Test Plan (STP) doc | All | 2023-12-17 | 2 | 2023-12-03
Prepare for End of semester demo | All | 2023-12-17 | 2 | 2023-12-03
Project presentation/demo (in class) | ALL | 2023-12-17 | 0 | 2023-12-17
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Adjusted Start = [Due Date]-(7*[Duration (Est. Wks)])